|  | District 4 Toastmasters Spring Conference 2007 Conference planning meeting Monday, May 7, 6:30-8:30pm |
| --- | --- |

| Elliotte Mao, Event Co-chair. [contact info] Joe Kent, Event Co-chair. [contact info] Contest facilitator mailing list: d4conference@googlegroups.com (private mailing list) Facilitator website: http://www.quia.com /files/quia/users/jhkiii/d4c/index.html Next planning meeting: Monday, May 14, 6:30-8:30pm, Silicon Valley Community Foundation, Ground floor meeting room, 1700 South El Camino Real, San Mateo, CA 94402 | 1. Introductions - Who needs to leave early? 2. Conference layout and itinerary - Conference in Shilpa Vir - Review plans, get input from all teams, do further mockups as needed - When does the hotel need final plans? 3. Decorations update - Conference in Shilpa Vir - Signage requirements: what to send Shilpa, how it fits together in the end - Get signage instructions to Shilpa by May 11 (or earlier!) - Shilpa will make 15 centerpieces. More needed? - Painters' tape preferred - Who is in charge of making signs? - Still need ladders, or can we ask hotel to help put up high items? 4. Sound, setup, cleanup update - Sadiq can't make it - Who else is in/out? Who can be facilities go-for person? Who can help Lucky with cleanup? - What do we do with stuff on Friday night? 5. Registration update - Joe Madley has all necessary access? - Managing contestant $10 discounts - Louise Wolfe can help at registration table - Badges: color coded; ribbons for conf chairs? - Protocol list 6. SAA Update - More team members needed? 7. Bookstore update - Supplies - Staff 8. Contest Chair and Chief Judge update - Get some contest supplies from Joe Kent - Ken will have remaining supplies @ next meeting? - Confirm timing light 9. Honor guard - Who will arrange it? 10. Still needed: hall of fame assistant 11. Opportunity drawing update - Team manned? - Joe Kent has ticket rolls - Give prizes to Derek/Jie - Prize listing/display - Guarding prizes - Storing prizes overnight 12. Candidate materials - Whose responsibility? - None on Friday night, since no Syracuse? 13. Credentials update - What times does this table need to be available? - Who's staffing it? - Prep work? 14. Promotional efforts - Final e-blast Wednesday, May 9; link to website - Distribute latest flyer in club meetings - Any final updates for website? 15. Facility status - Food order placed 16. Guest speakers - Rose to assign 4 division governors to be SAA/room support for guest speakers. What are the assignments? 17. Program - Folders ordered? - Business card inserts needed? - What material is still missing? (Better photos needed? Bud Everts photo?) - Resolution on printing cost? - Detailed, minute-by-minute schedule of events needed - Conference evaluation forms 18. Confirm next meeting venue |
| --- | --- |